## Sheet1
New System Plans
Tasks | Start Date | End Date | Duration
Come up with a list of computer hardware items needed for building the new system | 2022-03-25 | 2022-03-26 | 1
Buy the items from the list | 2022-03-27 | 2022-03-30 | 3
Assemble the computer and set up the basics of the system | 2022-03-31 | 2022-04-02 | 2
Meeting with golf course staff | 2022-04-03 | 2022-04-04 | 1
Install the software that the golf course prefers to use | 2022-04-04 | 2022-04-05 | 1
Train the staff of the golf course on how to use the system and its software | 2022-04-06 | 2022-04-11 | 5
Collect data of all members | 2022-04-12 | 2022-04-14 | 2
Arrange the data | 2022-04-15 | 2022-04-17 | 2
Build a database for the members | 2022-04-18 | 2022-04-30 | 12
Build a database for booking | 2022-05-01 | 2022-05-08 | 7
Build a database for maintainance | 2022-05-09 | 2022-05-12 | 3
Proofread | 2022-05-13 | 2022-05-15 | 2
Final Report | 2022-05-16 | 2022-05-18 | 2
44645
|  |  |  | Assigned Tasks to employees |  | Budget Plans | Budget Plans
|  |  |  | Names | Tasks
|  | Ethan |  | All Team Members | List all necessary computer components
|  | Becca |  | Chris | Buy the items on the list
|  | Steve |  | Kyle
|  | Chris |  | All Team Members | Assemble the computers and set up the basics
|  | Kyle |  | All Employees including golf staff | Meeting with golf staff for software choice
|  | Tristan |  | Ethan | Install the software
|  | All Team Members |  | Tristan
|  | All Employees including golf staff |  | Becca | Collect data from all members
|  | Golf Staff |  | Chris
Golf Staff
|  |  |  | Steve | Arrange data
Kyle
Golf Staff
|  |  |  | Steve | Creat database for members
Ethan
Tristan
Golf Staff
|  |  |  | Becca | Create database for booking
Chris
Kyle
Golf Staff
|  |  |  | Tristan | Create database for maintainance
Steve
Golf Staff
|  |  |  | All Employees including golf staff | Proof Read
|  |  |  | All Team Members | Report