## Sheet1
Initial Gantt Chart |  |  |  | Resource management
Tasks | Start_Date | End_Date | Duration | Task | Assigned
Feasibility Design | 2022-03-25 | 2022-03-26 | 1 | Feasibility Design | Manager
Indentify problems | 2022-03-26 | 2022-03-28 | 2 | Indentify problems | Manager and Team
Make team roles | 2022-03-27 | 2022-03-28 | 1 | Make team roles | Manager and Team
Set up development enviroments | 2022-03-28 | 2022-03-30 | 2 | Set up development enviroments | Team
Build system | 2022-03-30 | 2022-04-09 | 10 | Build system | Manager and Team
Code testing | 2022-04-10 | 2022-04-12 | 2 | Code testing | Code tester (Mikael)
Proofread | 2022-04-13 | 2022-04-14 | 1 | Proofread | Proofreader (Kyle)
Immigrate to main system | 2022-04-14 | 2022-04-17 | 3 | Immigrate to main system | Manager and Team
Final Report | 2022-04-17 | 2022-04-18 | 1 | Final Report | Manager